## osint group project
OSINT Group Project
Manage any type of project. Assign owners, set timelines and keep track of where your project stands.
App and Documentation
Name | Subitems | Status | Due date | Priority | Timeline - Start | Timeline - End
Test App |  | Done | 2025-04-24 | Critical ⚠️️ | 2025-04-23 | 2025-04-24
Make Presentation |  | Done | 2025-04-25 | High | 2025-04-24 | 2025-04-25
SUBMIT! |  | Done | 2025-04-25 | Critical ⚠️️ | 2025-04-25 | 2025-04-25
Finalize Documentation |  | Done | 2025-04-25 | Medium | 2025-04-25 | 2025-04-25
App works! |  | Done | 2025-04-25 | High | 2025-04-24 | 2025-04-24
Initial App Creation |  | Done | 2025-04-22 | High | 2025-04-21 | 2025-04-23
Implement APIs into App |  | Done | 2025-04-24 | Medium | 2025-04-21 | 2025-04-22
|  |  | 2025-04-22 to 2025-04-25 |  | 2025-04-21 | 2025-04-25
Research
Name | Subitems | Status | Due date | Priority | Timeline - Start | Timeline - End
What are we doing? |  | Done | 2025-04-19 | Low | 2025-04-18 | 2025-04-19
Find Data Sources |  | Done | 2025-04-21 | Medium | 2025-04-20 | 2025-04-21
Register for needed APIs |  | Done | 2025-04-22 | Low | 2025-04-21 | 2025-04-21
|  |  | 2025-04-19 to 2025-04-22 |  | 2025-04-18 | 2025-04-21