## osint project risk re
OSINT Project Risk Report
Use this risk register to manage and mitigate the risks across your projects
App
Name | Description | Implications | Risk status | Probability | Impact | Risk Level | Risk response
App fails during testing | The app fails to function at all during testing | Extreme Delay of Project | Mitigated | Unlikely | Severe | High | Avoid
App not fully implemented | App is missing/lacking in features for full points | Decrease in grade | Mitigated | Possible | Minor | Low | Accept
API
Name | Description | Implications | Risk status | Probability | Impact | Risk Level | Risk response
APIs become unavailable | The online sources go down and become unusable | Extremely BAD! | Mitigated | Possible | Severe | High | Transfer
Any of the API are not Free | Some API are commercial and only are available if you pay | Might not be able to use the API/Data Source | Mitigated | Possible | Moderate | Medium | Transfer
General Risks
Name | Description | Implications | Risk status | Probability | Impact | Risk Level | Risk response
Random Delay | Anything that delays submission (power outage, canvas goes down, etc) | Late submission | Mitigated | Unlikely | Moderate | Medium | Accept
Loss of files | Files get deleted/corrupted before submission | Incomplete Submission | Mitigated | Unlikely | Severe | High | Avoid